## Sheet1
Contract Reference | DATA Set | Number of Data Elements in FASAMS | Number of Data Elements not in FASAMS | Expected Integration Date (Subject to Change)
Guidance Document 16 | FACT | 21 | 0 At the last meeting it was decided the four outstanding elements were no longer needed. Everything is in FASAMS now. | 2020-01-01
Guidance Document 32 | CAT | 21 | 2 1. Participating in Gainful Activity - Requires definition of gainful activity 2. Discharged and Had a Removal From Home Due to Child Welfare Involvement - needs OCW Interface | 2020-01-01
Template 4 Supplemental | Behavioral Health Catalog of Care | 14 | 3 1. Able to Bill Health Insurance - Unaware of a field in FASAMS that defines this ------------------------------Still Requires Research-------------------------------- Unable at this time to determine if a Join can be accurately made to the Acute Care DB and provide the following information: 2. Capacity 3. DCF Funded Capacity - Potential Calculation for DCF Funded Capacity is Subcontract Funded Amount / Rate = DCF Funded Capacity | 2020-07-01
Template 11 | ME Monthly Progress Report | Already in FASAMS |  | 2019-09-01
Template 12 | ME Monthly Expenditure Report |  |  | 2020-07-01
Template 13 | ME Monthly Carry Forward Expenditure Report |  |  | 2020-07-01
Template 16 | Women's Special Funding Report | 17 | 8 *Information on the children that the women may be parenting may not be in FASAMS. Even if that information is in FASAMS we currently do not have a way of joining the Parent to the Child. * 1. Parenting a child 0 to 5 * 2. Parenting a child 6 to 17 3. Expected Due Date (being implemented) 4. Actual Due Date (being implemented) 5. Birth Date (being implemented) 6. Child Welfare Involved - needs OCW interface 7. Positive Urine Screen for the Month 8. Parenting Interventions This Month (Number) | 2020-01-01
Template 17 | FIT | 33 of the elements are collected in FASAMS 25 Items are Collected by FSFN 58 Fields in both Systems 4 new values to be added to code table accounts for 10 Fields 6 Fields to be deleted | Code values to be added by 07/01/19 CLIENT Table (accounts for 2 fields) FSFN CASE NUMBER FSFN IDENTIFICATION NUMBER FOR ENROLLED MEMBER TREATMENT EPISODE table (accounts for 8 fields in total) DLA-20 (accounts for 4 fields) AAPI (accounts for 4 fields) Fields to be removed per FIT program (6 fields) FIT REFERRAL DATE "CONTINUING ENROLLMENT YES OR NO" DATE DISCHARGE SUMMARY COMPLETED DOMESTIC VIOLENCE HISTORY ACE DATE ACE SCORE | FASAMS will ready to report on most FIT contract measures as of July 1, 2019. MEs and providers may need 6 months to add FSFN case number and Person ID, and DLA-20 and AAPI to their systems. Measures that use OCW data requires development and coordination with OCW and OITS. Anticipate having pilot measures in place by 01/01/20.
Template 21 | Care Coordination | 24 | 24 of 25 items necessary for CC are captured in FASAMS as long as the ME uses identifies a person receiving CC as part of service events. FASAMS is unable to determine whether an individual meets one of the major priority groups. We would need to add a field or a modifier to the client or treatment episode records to group persons as: - Adult acute care high utilizers - Individuals discharged from a SMHTF - Individual awaiting placement in a SMHTF - Adults with multiple arrests/incarceration/ involuntary placement - Caretakers/parents involved with child welfare - Other as approved by the Department (SPECIFY) | 09/30/19